## Summary Dashboard
Hospital Ward Pre-Handover Inspection Dashboard
WARD INSPECTION METRICS
Inspection Zone | Total Items | Passed | Failed | Pending | N/A | Completion %
Ward Offices (APN/NO & WM) | 24 | 0 | 0 | 0 | 0 | 0%
Patient Cubicle (6-Bed Room) | 31 | 0 | 0 | 0 | 0 | 0%
Total Ward Summary | 55 | 0 | 0 | 0 | 0 | 0%
OVERALL PASSED ITEMS |  |  | TOTAL DEFECTS FOUND
0 |  |  | 0

## Settings_Ref (hidden)
Status Options
Pass
Fail
Pending
N/A

## Ward Office Checklist
Pre-Handover Snagging Checklist: Ward Offices (APN/NO & WM Rooms)
Note: Select Pass, Fail, Pending, or N/A from the dropdown list in the Status column.
Item ID | Category | Element / Feature | Layman Checking Instructions (Look, Touch, Try) | Status | Notes / Defect Details | Target Location
OFF-01 | Finishes | Ceiling Panels | Look up at the ceiling tiles. Check for any water stains, dark smudges, dirty fingerprints, open gaps, or cracked panels. |  |  | Both Offices
OFF-02 | Finishes | Wall Paint & Surface | Check paint coverage. Look closely around door frames, light switches, and corners for scratches, chips, or plaster cracks. |  |  | Both Offices
OFF-03 | Finishes | Vinyl Flooring | Walk across the entire room. Check if the vinyl feels completely flat and smooth. Look for bubbles, tears, or unglued edges. |  |  | Both Offices
OFF-04 | Finishes | Skirt / Bottom Trim | Ensure the plastic border trim where the wall meets the floor is glued completely tight all the way around without open gaps. |  |  | Both Offices
OFF-05 | Finishes | Wall Glazing / Glass | Check any interior glass windows or glass wall partitions. Ensure they are totally clean, scratch-free, and sealed tightly in frames. |  |  | Both Offices
OFF-06 | Doors & Locks | Door Operation & Closer | Open the door fully and release it. Check if the door closer shuts the door smoothly, securely, and quietly on its own without slamming. |  |  | Both Offices
OFF-07 | Doors & Locks | Door Cosmetic Damage | Inspect both sides of the door surface and edges for dents, structural scratches, or missing finish. |  |  | Both Offices
OFF-08 | Doors & Locks | Door Protection Plates | Check the bottom kickplates and push plates. Ensure they are cleanly aligned and securely screwed/attached to the door. |  |  | Both Offices
OFF-09 | Doors & Locks | Lock & Keypad/Badge | Try the key, keypad, or badge swipe 3 times. Ensure it locks and unlocks easily. Turn internal handle to confirm escape route is always clear. |  |  | Both Offices
OFF-10 | Doors & Locks | Vision Panel Glass | Look at the small window embedded in the door. Is the glass perfectly clean, unbroken, and firmly fixed within its molding? |  |  | Both Offices
OFF-11 | Doors & Locks | Hinges | Listen closely while moving the door back and forth. Ensure there are no squeaking, scraping, or grinding sounds. |  |  | Both Offices
OFF-12 | Lighting | Wall Switches | Verify all wall switches are mounted perfectly straight, clean, and positioned at a uniform, comfortable height. |  |  | Both Offices
OFF-13 | Lighting | Switch Operation | Click every single switch on and off. Make sure the correct lights respond (e.g., separate switches for main lights vs. desk task lights). |  |  | Both Offices
OFF-14 | Lighting | Flickering & Noise | Turn all office lights on and stand quietly. Ensure there is zero micro-flickering, blinking, humming, or buzzing from the ceiling fixtures. |  |  | Both Offices
OFF-15 | Lighting | Dimming Controls | If dimmers are installed, turn the knob/slider up and down slowly. Ensure the light fades smoothly without flashing or shutting down abruptly. |  |  | Both Offices
OFF-16 | Lighting | Light Color Balance | Look up at all light fixtures simultaneously. Ensure they all emit the exact same shade of crisp white light (no mismatched yellow bulbs). |  |  | Both Offices
OFF-17 | Lighting | Shadows / Blinding Glare | Sit where the office desks will be. Ensure light falls clearly over the workspace without creating blinding reflections or casting heavy shadows. |  |  | Both Offices
OFF-18 | Furniture | Cabinet Counts | Count the installed units to match the plan: APN Office needs 3 floor cabinets (FLC) + 3 wall units (WHC). WM Office needs full-height cabinets (FHC). |  |  | Both Offices
OFF-19 | Furniture | Doors & Drawers | Open and close every single cabinet door and drawer. Ensure they slide smoothly, latch tightly, and align perfectly flush. |  |  | Both Offices
OFF-20 | Furniture | Workmanship & Edges | Run your hands safely along the edges of built-in counters and cabinets. Ensure no sharp corners, laminate peel, or loose handles exist. |  |  | Both Offices
OFF-21 | Furniture | Wall-Unit Anchor Strength | Give the wall-hung cabinets a gentle but firm tug from underneath. Ensure they are completely solid and securely anchored to the wall. |  |  | Both Offices
OFF-22 | Building Services | Power Sockets | Locate all electrical outlets on walls. Verify the plastic cover plates are perfectly straight and firmly screwed flush against the drywall. |  |  | Both Offices
OFF-23 | Building Services | Dataports (HAIT) | Find the network/computer internet jacks. Ensure the plastic casing is entirely intact, clean inside, and free of construction paint. |  |  | Both Offices
OFF-24 | Building Services | Communication (PABX) | Locate the telephone/fax line wall plug points. Ensure they are completely uncovered and fully accessible (not blocked by cabinetry). |  |  | Both Offices

## Patient Cubicle Checklist
Pre-Handover Snagging Checklist: Patient Cubicle (6-Bed Room 1A/1B)
Note: Select Pass, Fail, Pending, or N/A from the dropdown list in the Status column.
Item ID | Category | Element / Feature | Layman Checking Instructions (Look, Touch, Try) | Status | Notes / Defect Details | Target Location / Bed Column
CUB-01 | Finishes | Ceiling Panels / Paints | 1. Paints: Verify uniform coverage and color; check for bubbling, peeling, or water stains. 2. Panels: Verify flat alignment with no gaps or water stains. Ensure cutout edges are cleanly finished. |  |  | Ceiling Area
CUB-02 | Finishes | Ceiling Hoist Rail | 1. Rail Fit: Check for gaps between the hoist rail and ceiling panels. 2. Operation: Verify the hoist slides smoothly. |  |  | Ceiling Area
CUB-03 | ACMV | Air Supply Diffusers | Look up at the square metal vents that blow fresh air into the room. Check that the white frames are screwed flush tightly to the ceiling grid without gaps. Look inside the fins—make sure there are no black smudges, fingerprint marks, or thick construction dust blocking the air paths. |  |  | Ceiling Area | FM
CUB-04 | ACMV | Return Air Grilles | Look up at the slatted intake grilles that pull air out of the room. Stand directly under them for 5 seconds—listen closely to make sure they do not make a high-pitched whistling, rattling, or vibrating sound while the air system is running. |  |  | Ceiling Area | FM
CUB-05 | Finishes | Perimeter Glass & Frames | Check surfaces for scratches, chips, or cracks; ensure zero gaps, peeling, or punctures. |  |  | Window Side
CUB-05 | Finishes | Walls & Wall Glazing | 1. Wall: Check paint finish. Confirm zero visible dry cracks or structural chips. 2. Glazing: Check glass for cleanliness/damage and ensure all surfaces are free of scratches, chips, cracks, gaps, peeling, or punctures. |  |  | Walls/Windows
CUB-06 | Finishes | Bedhead Wall Protection | Verify that the bedhead wall bumper rail is securely installed at the correct height to prevent bed impact damage. |  |  | All 6 Bed Spaces
CUB-07 | Finishes | Vinyl Sheet Floor & Skirt | Inspect floor for unevenness or bubbling, ensuring all weld lines are flush and coved skirting is tightly sealed. |  |  | Floor Area
CUB-08 | Finishes | Window Curtains | Test curtains to ensure they open and close fully without jamming, and verify the fabric is clean and undamaged. |  |  | Window Side
CUB-09 | Finishes | Privacy Curtain Tracks | Test curtains to ensure they open and close fully without jamming, and verify the fabric is clean and undamaged. |  |  | All 6 Bed Spaces
CUB-10 | Lighting | Switches & Plates | Verify switches, and plates are level, securely mounted, no loose fittings or sunken plates. |  |  | All 6 Bed Spaces
CUB-11 | Lighting | Switch Mapping | Test switches to confirm correct mapping for overhead and bed reading lights. |  |  | All 6 Bed Spaces
CUB-12 | Lighting | Flickering & Noise | Turn fixtures on, check for flickering lights or panel humming. |  |  | Entire Cubicle
CUB-13 | Lighting | Dimming Adjustments | Test night dimmers to ensure smooth, flicker-free dimming. |  |  | Control Switches
CUB-14 | Lighting | Color & Shadow Uniformity | Verify uniform brightness and color, ensure no dark spots in clinical patient zones. |  |  | Entire Cubicle
CUB-15 | Building Services | Vertical Bedhead Trunk | Verify bedhead panel height and configuration match layouts, with zero sharp edges or wall gaps. |  |  | All 6 Bed Spaces
CUB-16 | Building Services | Mounting Blades / Arms | Verify suspended equipment arms are securely wall-mounted without shaking and rotate smoothly. |  |  | All 6 Bed Spaces
CUB-17 | Building Services | Dataports (HAIT) | Verify data ports are flush and level, and the outer casing is undamaged and not recessed. |  |  | All 6 Bed Spaces
CUB-18 | Building Services | Power Outlets & Plugs | Verify power outlet quantities, labeling, and color-coding are correct, and plates are secure and flush. |  |  | All 6 Bed Spaces
CUB-19 | Building Services | USB Charging Ports | Visually check that the dedicated USB slot modules are undamaged, securely clipped in place, and level. |  |  | All 6 Bed Spaces
CUB-20 | Building Services | Nurse Call Interface | Locate the emergency red button / pull-string interface plug. Click or pull it to confirm visual response signals trigger successfully. |  |  | All 6 Bed Spaces
CUB-21 | Building Services | Medical Gas Outlets (O2) | Verify correct gas type, quantity, position, and color-coded labels; ensure outer rings are secure with zero leakage. |  |  | All 6 Bed Spaces | combine?
CUB-22 | Building Services | Medical Vacuum / Suction | Verify correct gas type, quantity, position, and color-coded labels; ensure outer rings are secure with zero leakage. |  |  | All 6 Bed Spaces
CUB-23 | Building Services | Housekeeping / Spared Sockets | Verify power outlet quantities, labeling, and color-coding are correct, and plates are secure and flush. |  |  | Cubicle Common Walls
CUB-24 | Sanitary Fitments | Wash Hand Basin (LW-HH) | Run the water faucet tap fully for 15 seconds. Ensure water drains away rapidly. Look underneath to confirm absolutely zero pipe leaks. |  |  | Sink Alcove Zone
CUB-25 | Sanitary Fitments | IPS Backing Panels | Check the smooth plastic access panels directly behind the sink basin. Ensure they are cleanly caulk-sealed to keep water out of walls. |  |  | Sink Alcove Zone
CUB-26 | Sanitary Fitments | Manual Glove Dispenser | Confirm the stainless steel or plastic glove box bracket frame is bolted solidly to the wall structure with zero wiggle. |  |  | Sink Alcove Zone
CUB-27 | Sanitary Fitments | Auto Soap Dispenser | Wave your hand directly beneath the touchless soap module sensor. Ensure the device clicks or lights up indicating battery/power is live. |  |  | Sink Alcove Zone
CUB-28 | Sanitary Fitments | Paper Towel Dispenser | Give the paper towel cabinet casing a firm pull. Ensure it is anchored cleanly and the bottom slot dispenses without catching. |  |  | Sink Alcove Zone
CUB-29 | Miscellaneous | Ward Wall Clock (CK2) | Look at the main ward clock. Ensure it is hung perfectly level, the face is scratch-free, and the hands are actively moving. |  |  | Shared Central Wall
CUB-30 | Miscellaneous | TV Support Pole & Plugs | Locate the structural support pole for the 55-CM TV. Shake it firmly—must hold a heavy television. Check nearby electricity/coaxial sockets. |  |  | Shared Central Wall
CUB-31 | Miscellaneous | Bed Identification | Look at the main ward clock. Ensure it is hung perfectly level, the face is scratch-free, and the hands are actively moving. |  |  | Shared Central Wall